## Detailed_Bug_Report
Bug ID | User Type | Requirement ID | Bug Title | Module | Feature | Environment | Build/Version | Browser | Severity | Priority | Defect Type | Preconditions | Test Data | Steps to Reproduce | Expected Result | Actual Result | Error Message | Evidence | Status | Confidence Level
BUG-001 | standard_user | Not Available | Product card alignment inconsistent | Inventory | Product Listing | Not Available | Not Available | Not Available | Low | Low | UI | User logged in | Not Available | Open inventory page | Cards aligned consistently | Cards appear misaligned | Not Available | Screenshot review | Open | Medium
BUG-002 | standard_user | Not Available | Inconsistent product naming | Catalog | Product Display | Not Available | Not Available | Not Available | Low | Low | UI/Data | User logged in | Not Available | Review product names | Consistent naming convention | Naming inconsistent | Not Available | Screenshot review | Open | Medium
BUG-003 | standard_user | Not Available | Navigation drawer too wide | Navigation | Side Menu | Not Available | Not Available | Not Available | Low | Low | UX | User logged in | Not Available | Open side menu | Responsive drawer width | Drawer occupies excessive area | Not Available | Screenshot review | Open | Medium
BUG-004 | standard_user | Not Available | Close icon alignment issue | Navigation | Side Menu | Not Available | Not Available | Not Available | Low | Low | UI | Side menu open | Not Available | Observe close icon | Proper alignment | Alignment issue observed | Not Available | Screenshot review | Open | Medium
BUG-005 | standard_user | Not Available | Cart badge not visible | Cart | Cart Indicator | Not Available | Not Available | Not Available | Medium | Medium | UI/Functional | User logged in | Not Available | View cart icon | Cart count visible when applicable | Badge not visible | Not Available | Screenshot review | Open | Low
BUG-006 | standard_user | Not Available | Image aspect ratios inconsistent | Inventory | Product Images | Not Available | Not Available | Not Available | Low | Low | UI | User logged in | Not Available | Open inventory page | Uniform image dimensions | Different image ratios observed | Not Available | Screenshot review | Open | Medium
BUG-007 | standard_user | Not Available | Description truncation risk | Inventory | Product Description | Not Available | Not Available | Not Available | Medium | Medium | Responsive UI | User logged in | Not Available | Review long descriptions | Text displayed correctly | Potential truncation/overflow | Not Available | Screenshot review | Open | Low
BUG-008 | standard_user | Not Available | Filter icon not working | Sorting | Filter | Not Available | Not Available | Not Available | Medium | High | Functional | User logged in | Not Available | Click filter icon | Filtering works | Filtering not working | Not Available | User observation | Open | High
BUG-009 | standard_user | Not Available | Hover state unclear in menu | Navigation | Menu | Not Available | Not Available | Not Available | Low | Low | UI | Menu open | Not Available | Hover menu items | Visual feedback displayed | No clear hover state | Not Available | User observation | Open | Medium
BUG-010 | standard_user | Not Available | No breadcrumb navigation | Navigation | Navigation Controls | Not Available | Not Available | Not Available | Low | Low | UX | User logged in | Not Available | Navigate catalog | Breadcrumb available if required | Breadcrumb absent | Not Available | Observation | Open | Low
BUG-011 | standard_user | Not Available | Session persistence test required | Authentication | Session | Not Available | Not Available | Not Available | Not Available | Not Available | Needs Investigation | Logged in | Not Available | Verify refresh/login session | Not Available | Not Available | Not Available | No evidence | Pending | Low
BUG-012 | standard_user | Not Available | Sort order verification needed | Sorting | Product Sort | Not Available | Not Available | Not Available | Not Available | Not Available | Needs Investigation | Logged in | Not Available | Verify sorting | Not Available | Not Available | Not Available | No evidence | Pending | Low
BUG-013 | standard_user | Not Available | Duplicate add-to-cart verification | Cart | Cart | Not Available | Not Available | Not Available | Not Available | Not Available | Needs Investigation | Logged in | Not Available | Add same product repeatedly | Not Available | Not Available | Not Available | No evidence | Pending | Low
BUG-014 | standard_user | Not Available | Responsive mobile layout validation | Responsive UI | Mobile View | Not Available | Not Available | Not Available | Not Available | Not Available | Needs Investigation | Application available | Not Available | Open on mobile viewport | Not Available | Not Available | Not Available | No evidence | Pending | Low
BUG-015 | error_user | Not Available | Remove button not working after adding product | Cart | Remove Item | Not Available | Not Available | Not Available | High | High | Functional | Product added to cart | Any product | Add product then click Remove | Product removed | Product not removed | Not Available | User report | Open | High
BUG-016 | error_user | Not Available | Last name field not working in checkout | Checkout | Customer Information | Not Available | Not Available | Not Available | High | High | Functional | Checkout step one opened | Last name value | Enter last name | Field accepts input | Field not accepting input | Not Available | User report | Open | High
BUG-017 | error_user | Not Available | Finish button not working | Checkout | Order Completion | Not Available | Not Available | Not Available | Critical | High | Functional | Checkout overview page | Valid order | Click Finish | Order completes | Nothing happens | Not Available | User report | Open | High
BUG-018 | performance_glitch_user | Not Available | Login slower than usual | Authentication | Login | Not Available | Not Available | Not Available | Medium | Medium | Performance | Login page open | Valid credentials | Login | Timely login | Noticeable delay | Not Available | User report | Open | Medium
BUG-019 | performance_glitch_user | Not Available | Order can be placed with no items | Checkout | Order Processing | Not Available | Not Available | Not Available | Critical | High | Functional | Cart empty | No items | Attempt checkout | Checkout blocked | Order proceeds | Not Available | User report | Open | High
BUG-020 | performance_glitch_user | Not Available | Reset app state not reflected in UI | Application State | Reset App State | Not Available | Not Available | Not Available | High | High | Functional | State changed | Not Available | Reset app state | UI refreshed | UI unchanged | Not Available | User report | Open | High
BUG-021 | performance_glitch_user | Not Available | Sorting takes longer than usual | Sorting | Product Sort | Not Available | Not Available | Not Available | Medium | Medium | Performance | Inventory loaded | Not Available | Apply sort | Quick response | Sorting delayed | Not Available | User report | Open | Medium
BUG-022 | performance_glitch_user | Not Available | Back Home button slow response | Navigation | Back Home | Not Available | Not Available | Not Available | Medium | Medium | Performance | Checkout complete page | Not Available | Click Back Home | Navigate promptly | Delayed navigation | Not Available | User report | Open | Medium
BUG-023 | problem_user | Not Available | All product images are same | Inventory | Product Images | Not Available | Not Available | Not Available | High | High | Data/UI | Logged in | Not Available | View products | Unique images displayed | Same image repeated | Not Available | User report | Open | High
BUG-024 | problem_user | Not Available | Product hyperlinks not working | Inventory | Product Details Navigation | Not Available | Not Available | Not Available | High | High | Functional | Inventory available | Not Available | Click product links | Correct page opens | Link fails | Not Available | User report | Open | High
BUG-025 | problem_user | Not Available | Sorting not working properly | Sorting | Product Sort | Not Available | Not Available | Not Available | High | High | Functional | Products available | Not Available | Apply sorting | Correct sorting result | Incorrect sorting | Not Available | User report | Open | High
BUG-026 | problem_user | Not Available | Method name exposed in description | Inventory | Product Description | Not Available | Not Available | Not Available | Low | Low | Content Defect | Inventory loaded | Not Available | View product description | User-friendly text | Technical method exposed | Not Available | User report | Open | High
BUG-027 | problem_user | Not Available | Product name not displayed properly | Inventory | Product Name | Not Available | Not Available | Not Available | Medium | Medium | UI | Inventory loaded | Not Available | View product name | Correct display | Improper display | Not Available | User report | Open | High
BUG-028 | problem_user | Not Available | Add to cart not working for some products | Cart | Add To Cart | Not Available | Not Available | Not Available | High | High | Functional | Inventory loaded | Any affected product | Click Add to Cart | Item added | Item not added | Not Available | User report | Open | High
PROMPT
Role:Act like an experienced Artifact DesignerTask: Create the excel sheet for my bug report using the inputed excel sheet as i have uploaded the excel sheet Input: OUtput: follow the below pattern to create the excel sheet using the below columns Bug ID:User Type:Requirement ID:Bug Title:Module:Feature:Environment:Build/Version:Browser:Severity:Priority:Defect Type:Preconditions:Test Data:Steps to Reproduce:Expected Result:Actual Result:Error Message:Evidence:Status: RULES 1. Do not assume a defect exists only because a test failed.2. First classify the failure.3. Distinguish application defects from automation failures.4. Do not invent missing information.5. If information is unavailable, write "Not Available".6. Steps must be clear and reproducible.7. Expected and actual results must be clearly separated.8. Assign severity based on business impact.9. Assign priority based on urgency and release impact.10. Use professional defect-management terminology.11. Do not include sensitive or real user information.12. Provide confidence level for defect classification.